## Sheet1
Person	Thing	Reason	Date	Time spent
Max Briggs	Meeting with Todd Cleek	Project ideas	01/08/16	60
Todd Cleek	Meeting with Todd Cleek	Project ideas	01/08/16	60
Max Briggs	Email to Todd Cleek	Looking for contacts	08/21/16	25
Greg Bliek	Project meeting	Rough planning for project	09/04/16	15
Max Briggs	Call to John Schwartz	Left message	09/11/16	1
Max Briggs	Call to John Schwartz	consulting about pipe size, suppllier	09/11/16	5
John Schwartz	Call to John Schwartz	consulting about pipe size, suppllier	09/11/16	5
Max Briggs	Meeting with Brian Hehr	request for project by Brian	09/14/16	30
Brian Hehr	Meeting with Brian Hehr	request for project by Brian	09/14/16	30
Jeff Briggs	Meeting with Brian Hehr	adult supervision	09/14/16	30
Max Briggs	meeting	preliminary wookbook meeting	07/10/17	50
Shalome Briggs	meeting	Buddy – preliminary wookbook meeting	07/10/17	50
Eric Hazard	meeting	preliminary wookbook meeting	07/10/17	50
Max Briggs	Email to Greg Bliek	asking about availability of project	07/11/17	10
Max Briggs	Message to Eric Hazard	request meeting to review proposal	07/12/17	2
Max Briggs	Meeting	preliminary wookbook meeting	07/12/17	60
Shalome Briggs	Meeting	Buddy – preliminary wookbook meeting	07/12/17	60
Eric Hazard	Meeting	preliminary wookbook meeting	07/12/17	60
Max Briggs	Call	wood quote from Diamond Pacific	07/14/17	13
Max Briggs	Meeting	consulting about viability of project	07/14/17	20
Greg Bliek	Meeting	consulting about viability of project	07/14/17	20
Wyatt Briggs	Meeting	Buddy – consulting about viability of project	07/14/17	20
Max Briggs	Editing workbook	Finish proposal	07/14/17	45
Max Briggs	Meeting	turn in proposal to Mr Hazard	07/15/17	5
Max Briggs	Meeting	turn in proposal to Mr Sipe	07/27/17	60
Michael Sipe	Meeting	turn in proposal to Mr Sipe	07/27/17	60
Eric Hazard	Meeting	turn in proposal to Mr Sipe	07/27/17	60
Max Briggs	Call	Quote email address for Meek’s Lumber and Hardware	07/28/17	2
Max Briggs	Email	Sending quote request to Meeks’ Lumber Hardware	07/28/17	5
Max Briggs	Shopping	Getting prices from Home Depot	08/05/17	30
Max Briggs		turn in proposal to Dr Phipps	08/07/17	20
Mark Phipps		signing of proposal	08/07/17	5
Max Briggs	Shopping	Getting quote from Diamond Pacific	08/15/17	180
Shalome Briggs	Shopping	Getting quote from Diamond Pacific	08/15/17	180
Jason de Lemos	Advising	Giving material advice and quote from Diamond Pacific	08/15/17	20
Max Briggs	Final check	Getting final go-ahead from Greg Bliek	08/15/17	30
Greg Bliek	Final check	Giving me final go-ahead	08/15/17	30
Max Briggs	Call	Learning payment method for wood	08/18/17	2
Vicki Jensen	Call	Telling me payment method for wood	08/18/17	2
Max Briggs	Purchasing	Purchasing brackets from Diamond Pacific	08/18/17	60
Max Briggs	Measuring	Measuring sidewalk height for concrete footings	08/21/17	60
Max Briggs		Building concrete forms and prepping materials	08/21/17	195
Jeff Briggs		Building concrete forms and prepping materials	08/21/17	195
Max Briggs		Digging post holes, pouring concrete, setting brackets, picking lumber	08/22/17	600
Jeff Briggs		Digging post holes, pouring concrete, setting brackets, picking lumber	08/22/17	600
Matt Haye		Digging post holes, pouring concrete, setting brackets	08/22/17	330
Max Briggs		Measuring for upper distancing	08/23/17	45
Jeff Briggs		Measuring for upper distancing	08/23/17	45
Shalome Briggs		buying brushes	08/23/17	60
Jeff Briggs		buying brushes	08/23/17	60
Max Briggs		picking up tubs for paint	08/24/17	15
Shalome Briggs		picking up tubs for paint	08/24/17	15
Greg Bliek		accepting delivery of lumber and unplugging sprinker lines	08/24/17	30
Max Briggs		rectifying delivery problem and picking 2x4’s	08/24/17	45
Jeff Briggs		rectifying delivery problem and picking 2x4’s	08/24/17	45
Max Briggs		Taking off forms and cleaning up concrete	08/24/17	60
Jeff Briggs		Taking off forms and cleaning up concrete	08/24/17	60
Max Briggs		Scanning reciepts	08/24/17	20
Will Stonestreet		Staining	08/25/17	250
Max Briggs		Staining	08/25/17	250
Wyatt Briggs		Staining	08/25/17	250
Smith Briggs		Staining	08/25/17	180
Jason Kirby		Staining	08/25/17	75
Matt Buettner		Staining	08/25/17	150
Daniel Buettner		Staining	08/25/17	150
David Buettner		Staining	08/25/17	150
Mark Buettner		Staining	08/25/17	150
Maxwell Allen		Staining	08/25/17	140
Andrew Duncan		Staining	08/25/17	150
Matthew Duncan		Staining	08/25/17	150
John Duncan		Staining	08/25/17	150
Kelly Manos		Staining	08/25/17	90
Eric Manos		Staining	08/25/17	90
Isabella Gabrielli		Staining	08/25/17	180
Jeff Briggs		Cutting posts	08/25/17	180
Molly Briggs		Staining	08/26/17	150
Matt Stonestreet		Staining	08/26/17	66
Greg Stonestreet		Staining	08/26/17	66
Becky Stonestreet		Staining	08/26/17	66
Wyatt Briggs		Staining	08/26/17	150
Aidan Oddo		Staining	08/26/17	59
Max Briggs		Staining and cutting posts	08/26/17	720
Jeff Briggs		Cutting posts	08/26/17	720
Max Briggs		Setting up structure	08/29/17	600
Jeff Briggs		Setting up structure	08/29/17	600
Max Briggs		Updating time sheet	09/02/17	20
Max Briggs		Screwing pieces	09/04/17	240
Jeff Briggs		Screwing pieces	09/04/17	240
John Schwartz		Screwing pieces	09/04/17	240
Max Briggs		Buying 2x4 and screws	09/04/17	60
Jeff Briggs		Buying 2x4 and screws	09/04/17	60
Jeff Briggs		Cutting 2x4’s	09/06/17	40
Jeff Briggs		Staining 2x4’s	09/06/17	30
Max Briggs		Dropping off letter of recommendation envelopes	09/11/17	45